| System generation & Revenue Details |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Solar Roof Top Size: |  |  | 6.20 | Kw |  |  |  |  |  | [Total Kw] |  |  |  |  |  |  |  |
| Generation / Day : |  |  | 31Unit |  | Yearly Saving : |  | 83120Rupees |  |  | [Total Kw * 5] |  |  | [Sum of INR] |  |  |  |  |
| 1st Year Generation : |  |  | 10390Kwh |  | 25 Year Saving : |  | 2078000Rupees |  |  | [Sum of Kwh] |  |  | [Yearly Saving * 25] |  |  |  |  |
| Predicted Monthly Generation |  |  |  |  | Predicted Monthly Savings |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Graph from Generation Table for Month,Kwh |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Graph from Generation Table for Month, INR |  |  |  |  |  |  |  |
| Note | Predicted Generation is Indicative only. It may vary depending upon weather condition & Module Condition. Savings Calculated @ INR 8/Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Solar Plant Installation : Procedure & Time frame |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Steps | Procedure |  | Description |  |  |  |  | Time Period (Approx) |  |  |  |  |  |  |  |  |  |
| Step-1 | GEDA Registration |  | Start Registration process By Collecting Required Documents |  |  |  |  | 1-2 working Days |  |  |  |  |  |  |  |  |  |
| Step-2 | Document Verification |  | Verification of uploaded documents after registration |  |  |  |  | 4-5 Working days |  |  |  |  |  |  |  |  |  |
| Step-3 | Feasibility Approval |  | DISCOM will Give Feasibility Approval & issue Estimate of solar Meter after Document verification |  |  |  |  | 10- 15 Working days |  |  |  |  |  |  |  |  |  |
| Step-4 | IFP Drawing Approval Applicable for above 10kw |  | In this step HTSS will make an Electrical drawing and upload on IFP Portal For further installation process. |  |  |  |  | 15 - 20 Working days |  |  |  |  |  |  |  |  |  |
| Step-5 | Execution Work |  | After Getting all Approvals we will start plant execution work |  |  |  |  | 15 - 20 Working days |  |  |  |  |  |  |  |  |  |
| Step-6 | CEIG Inspection Approval Applicable for above 10kw |  | After Completing the Installation Process We will Apply for CEIG Inspection,CEIG inspector will physically come on site and verify all the parameters. |  |  |  |  | 15 - 20 Working days |  |  |  |  |  |  |  |  |  |
| Step-7 | Net Metering Process |  | Once we get CEIG Approval, we will prepare a file for net metering process and submit it to DISCOM for meter installation process |  |  |  |  | 30 - 45 Working days |  |  |  |  |  |  |  |  |  |
| Step-8 | Commissioning & Testing |  | After Installation and CEIG approval Testing procedure will be done by HTSS |  |  |  |  | 1-2 working Days |  |  |  |  |  |  |  |  |  |
| Step-9 | Completion of project |  | After testing, HTSS will handover the plant to the client |  |  |  |  | 1-2 working Days |  |  |  |  |  |  |  |  |  |
| Note | The procedure and timeframe mentioned above are approximate and may vary depending on various factors such as weather conditions, document processing delays, payments delay and approvals from concerned authorities. These timelines are provided as a general guideline and are not fixed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Solar Plant ROI Calculator (Input Parameters) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Parameter |  |  | Unit |  | Value |  | Notes |  |  |  |  |  |  |  |  |  |  |
| Project Capacity |  |  | kw |  | 6.20 |  | Size of plant |  |  |  |  |  |  |  |  |  |  |
| Installation Cost |  |  | ₹ |  | ₹ 2,82,100.00 |  | Total EPC cost |  |  |  |  |  |  |  |  |  |  |
| Average Daily Generation |  |  | Kwh/Kwp/day |  | 4 |  | Based on site data |  |  |  |  |  |  |  |  |  |  |
| Average Yearly Shutdown |  |  | Days |  | 30 |  | Plant Maintenace,Grid Side Maintenace,or any Emergancy Shutdowns |  |  |  |  |  |  |  |  |  |  |
| Electricity Tariff (Year 1) |  |  | ₹/Kwh |  | ₹ 8.00 |  | Current grid rate |  |  |  |  |  |  |  |  |  |  |
| Tariff Escalation |  |  | % |  | 3 |  | Expected yearly increase |  |  |  |  |  |  |  |  |  |  |
| Annual Power Degradation (After 1st Year) |  |  | % |  | 2 |  | Module efficiency drop (As per Modul Data Sheet) |  |  |  |  |  |  |  |  |  |  |
| Annual Power Degradation (From 3rd Year to 30 Years) |  |  | % |  | 0.5 |  | Module efficiency drop (As per Modul Data Sheet) |  |  |  |  |  |  |  |  |  |  |
| O&M Cost (Year 1) |  |  | ₹ |  | ₹ 2,821.00 |  | Maintenance cost |  |  | [Total Cost] * 1% |  |  |  |  |  |  |  |
| O&M Cost Escalation |  |  | % |  | 3 |  | Inflation in O&M |  |  |  |  |  |  |  |  |  |  |
| Project Life |  |  | Years |  | 30 |  | Standard for solar |  |  |  |  |  |  |  |  |  |  |